## Sheet1
Sidechains - Phase One |  |  | Resource | Estimate (d) | Carlton | Kevin | NodeDev | C# Dev | Tester | Notes
Sidechains: multisig input transaction |  |  | Carlton | 4 | 2 |  | 2 |  |  | federation logic is part of the input and output transaction
Sidechains: funding experience |  |  | Carlton | 4 | 2 |  |  | 2 |  | minting also with the withdrawal proof
Sidechains: coin minting |  |  | Carlton+Kevin | 12 | 3 | 3 | 3 | 3 |  | premine with some kind of lockup then released through OP_CODE/contract style logic
Sidechains: receiving funds |  |  | Carlton+NodeDev+C#dev | 22 | 6 |  | 6 | 10
Sidechains: inter chain verification |  |  | Carlton+NodeDev+C#dev | 17 | 5 |  | 6 | 6
Sidechains: spv proof |  |  | Kevin | 7 |  | 5 |  | 2
Sidechains: re-organization |  |  | Kevin+NodeDev | 16 | 8 |  | 6 | 2
Sidechains: transfer out of chain |  |  | Carlton+NodeDev+C#dev | 30 | 10 | 2 | 6 | 12
Sidechains: transfer into mainchain |  |  | Carlton+NodeDev+C#dev | 20 | 6 | 2 | 6 | 6
Sidechains: integration testing |  |  | Carlton | 6 | 6
Sidechains: uat |  |  | Tester | 6 |  |  |  |  | 6
Atomic Swaps |  |  | kevin | 4 |  | 3 |  | 1
Research time (phase 2 PoC) |  |  | Kevin+Carlton | 24 | 6 | 12 | 3 | 3
Blockchain Generation: Integration Test |  |  | NodeDev | 3 | 1 |  | 1 | 1
Blockchain Generation: Mainnet and RegTest Networks |  |  | NodeDev | 6 | 3 |  |  | 3
Blockchain Generation: CoinType changes |  |  | NodeDev | 3 |  |  | 3
Blockchain Generation: Coin Label in UI |  |  | C# dev, easy Angular change | 2 |  |  | 1 | 1
Blockchain Generation: Testing Wallet with Dual Coins |  |  | NodeDev | 3 |  |  | 3 |  |  | 1 day for initial testing
Blockchain Generation: Website
| Requirements |  | Carlton | 1 | 1
| Setup Project/Build |  | Carlton | 1 | 1 |  |  |  |  | * Include Test Manager add-in VSTS
| Build Site |  | C# dev | 3 |  |  |  | 3 |  | asp.net core, auto deployed through asp.net. Includes saving data
| Package Autobuild |  | C# dev | 3 |  |  |  | 3 |  | win/mac/linux - based on Jeremy's work
Blockchain Generation: switch from PoW to PoS testing |  |  | NodeDev | 2 |  |  | 2
Blockchain Customization: Consensus Rules Review |  |  | Carlton+Kevin+NodeDev | 6 | 2 | 2 | 2
Blockchain Customization: Other |  |  | Carlton+Kevin+NodeDev | 16 | 4 | 4 | 4 | 4 |  | Without these steps the sidechains will look identical to the mainchain
|  |  | Total man days | 221 | 66 | 33 | 54 | 62
Features |  | Area
Create a Blockchain |  | BG
| TestNet | BG
| RegTest | BG
| MainNet | BG
Create a Sidechain |  | BG
| TestNet | BG
| RegTest | BG
| MainNet | BG
Mine Sidechain |  | BG
Mine Blockchain |  | BG
Build Packages |  | BG
| Windows | BG
| Linux | BG
| Mac | BG
WalletSupport |  | BG
| Support Dual Currencies | BG
Consensus Rules Customization |  | BC
Other |  | BC
Fund a Sidechain |  | S
Receive Funds |  | S
Mint Coins |  | S
Transfer Out of Chain |  | S